## Sheet1
Sprint | Issue Type | Task | Issue description | Assign to | Status | Actual Efforts | Estimated Efforts | Comments
Sprint 1 (11th september - 24th spetmeber) | SP-8 | Research | Searching different student api | Joyal | completed | 3 | 4 | API link
| SP-9 | Research | Analyzing the suitable programming language for the project | Anuj | completed | 6 | 4 | Concluded with python programmimg
| SP-10 | Research | R&D on calling API | Joyal | completed | 7 | 8
| SP-11 | Design | Wireframe for Student database management system | Anuj | completed | 5 | 8 | Created desgin and added in user story
Sprint Delieverable
Sprint 2 (25th september - 08 november) | SP-12 | Test case | Test case for UI | Joyal | completed | 6 | 4
| SP-13 | Test case | Test case for backend | Joyal | completed | 6 | 4
| SP-14 | Database | Data soruce design | Anuj | completed | 2 | 8 | Desgin added in user story
| SP-15 | Design | Creating the Design patterns | Anuj | completed | 4 | 8
| SP-16 | Design | Making applicable patterns | Joyal | completed | 3 | 4
| SP-17 | Research | R&D on refactoring strategies. | Anuj | completed | 5 | 4
| SP-18 | Research | Research on testing tools and github understanding | Joyal | completed | 4 | 8 | JIRA Link
Sprint Delieverable
Sprint 3 (9th november - 14th november) | SP-19 | Research | Understanding of CRUD operation | Anuj | completed | 5 | 4
| SP-20 | UI | UI for displaying data from database | Anuj | completed | 6 | 3
| SP-21 | Backend | Backend for Create table | Joyal | completed | 3 | 5
| SP-22 | UI | UI for CRUD operation from database | Anuj | completed | 6 | 4
| SP-23 | Backend | Backend for insert operation | Joyal | completed | 5 | 3
| SP-24 | Backend | Backend for delete operation table | Joyal | completed | 4 | 3
| SP-25 | Backend | Backend for select & update table | Anuj | completed | 6 | 6
| SP-26 | Backend | Backend for additional features into the system | Anuj | completed | 5 | 5
| SP-27 | Test case | Test case execution | Joyal | completed | 2 | 4 | Testing Tool Link
| SP-28 | Documentation | Adding documents into the github | Joyal | completed | 4 | 4 | Github Link